SecureProfit Hub

Feature & Calculation Reference

Project & Profitability Management System for IT Security Consulting

Internal Presentation Material

Prepared: June 2026

# Table of Contents

- 1.  Executive Summary

- 2.  Technology & Architecture

- 3.  User Roles & Access

- 4.  Project Lifecycle

- 5.  Core Features by Module

- 6.  Calculations in the Application

- 7.  End-to-End Worked Example

- 8.  Accounting Integration (Xero)

- 9.  Security & Access Control

- 10. Presentation Preparation & Demo Flow

# 1. Executive Summary

SecureProfit Hub is a full-stack web application for an IT security consulting firm. It manages the entire journey of a project — from intake by the Sales team, planning by the Project Manager, execution by consultants, through to closing and invoicing — while monitoring profit margins in real time as consultants log billable man-days.

### Problems it solves

- Slow, manual visibility into project profitability (usually only known once the project ends).

- Timesheets, expenses, and invoicing scattered across many spreadsheets.

- Difficulty planning resource capacity and tracking consultant utilization.

- Error-prone invoicing and VAT recap calculations.

### Key value

- Project margin and cost are computed automatically from approved timesheets and expenses.

- A single source of truth for projects, resources, billing, and management reporting.

- Role-based access so each function only sees what is relevant.

- Direct Xero integration for issuing invoices and syncing payments.

# 2. Technology & Architecture

The application is built as a monorepo with a clear separation between the interface, the server, and the database.

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | React + Vite + TypeScript + Tailwind, Recharts charts | User interface, dashboards, forms, and visualizations |
| Backend | Node.js + Express, JWT authentication | Business logic, validation, and APIs |
| Database | PostgreSQL (via Prisma) | Stores projects, users, timesheets, and billing |
| API contract | OpenAPI 3 + schema validation | Keeps data consistent between server and interface |
| Integration | Xero Accounting API (OAuth2) | Invoice issuance & payment synchronization |

# 3. User Roles & Access

Every user has a role that determines the modules and data they can access. Summary of the main roles:

| Role | Main responsibility |
| --- | --- |
| Management (PMO Director) | Full access: all projects, approvals, and every financial figure. |
| Project Manager (PM) | Manages own projects, resources, and approves their team's timesheets. |
| Sales | Creates clients & projects (intake); manages commercial data of own projects. |
| Consultant | Logs own timesheets and updates task status. |
| Technical Writer | Same as consultant, for writing/reporting work. |
| Project Admin | Manages closing documents (BAST / Invoice / Contract). |
| Principal (3 types) | Supervises delivery teams (Consultant/TW/Admin) and approves their team members' project assignments — WITHOUT access to financial figures. |
| Finance | Read access to all projects/reports + VAT recap; uploads invoice/contract documents. |
| HR | People operations: employees, leave, skill matrix, bench — no financial access. |
| Site Admin | User administration and system audit logs. |

Important note: Principal, delivery (Consultant/TW), and HR roles never see contract value, cost, or margin. The Financials and Billing tabs are automatically hidden from them.

# 4. Project Lifecycle

A project moves through the following statuses:

DRAFT  ->  OBSERVATION  ->  ACTIVE  ->  PAUSE / COMPLETE  ->  CLOSED

| Status | Meaning | Who acts |
| --- | --- | --- |
| DRAFT | Initial intake by Sales (4 basic fields). | Sales |
| OBSERVATION | PM completes description, dates, revenue, man-days & cost. | Project Manager |
| ACTIVE | Project is running; timesheets & expenses begin. | Delivery team |
| PAUSE / COMPLETE | Project is paused or finished. | PM / Management |
| CLOSED | Project is fully closed. | Management |

New invoicing rule: a project can only be invoiced once it is ACTIVE or later (ACTIVE, PAUSE, COMPLETE, CLOSED). Projects still in DRAFT or OBSERVATION — i.e. not yet running — cannot issue invoices, push to Xero, or be marked INVOICED/PAID.

# 5. Core Features by Module

## 5.1 Role-Based Dashboards

Each role gets a dashboard tailored to its needs:

- Management: executive KPIs, profit trend, billing aging, at-risk projects, PM allocation.

- Project Manager: active projects, approval inbox, utilization, revenue vs profit, alerts.

- Sales: pipeline, revenue per client, profitability trend.

- Consultant/TW: log-time prompt, trend, and my-tasks list.

- Project Admin: closing-document inbox.

- HR: headcount, business-unit/role distribution, leave, bench, skill gaps.

## 5.2 Project Management & Its Tabs

Each project has a detail page with the following functional tabs:

- Overview — summary & editing of core data via a 'Review & Save' dialog.

- Timeline (Gantt) — task scheduling with drag-and-drop, resize, and dependency arrows.

- Tasks (WBS) — hierarchical work breakdown, multi-assignee, finish-to-start dependencies, billable flag.

- Resources — staffing of Consultant & Technical Writer teams, Project Admin, and other resources. When a PM assigns a Consultant or Technical Writer who reports to a Principal, that assignment must be approved by the Principal before it becomes active.

- RAID — register of Risk, Assumption, Issue, Dependency (delivery team only).

- Expenses — non-resource costs with an approval flow; only APPROVED items add to actual cost.

- Timesheets — all time entries on the project, with KPIs and bulk approval.

- Billing — payment milestones with %, DPP, VAT, total, due date, and invoice status.

- Financials — cost, profit, margin, burn rate, and forecast.

- Documents, Closing, Report, Survey, Workstreams, Activity — documents, closing, project reports, customer survey, workstreams, and audit trail.

## 5.3 Other Modules & Pages

| Module | Function |
| --- | --- |
| Clients | Client data management. |
| Timesheets (global) + bulk entry | Time logging & approval across projects; weekly bulk entry. |
| Reports | 10 ready-made reports with CSV/XLSX/PDF export. |
| Resource Planning | Weekly man-day load per business unit (with leave overlay). |
| Bench & Capacity | Unallocated consultants and team capacity. |
| Skill Matrix | Mapping of team skills and gap identification. |
| Invoice Planning | Billing projection per period (week/month) per business unit. |
| VAT Recap | 12-month + annual VAT recap from INVOICED/PAID invoices. |
| Performance Reviews | Performance appraisal with DRAFT -> SUBMITTED -> ACKNOWLEDGED flow. |
| Leaves & Org Chart | Leave management and organization chart. |
| Task Templates | Reusable WBS templates applied to new projects. |
| Settings | Configurable alert thresholds for dashboard notifications (low margin, budget overrun, invoice due soon, late timesheets); in-app only. |

# 6. Calculations in the Application

This section explains all core formulas the application uses to compute cost, profit, margin, tax, and billing. All currency values are in Rupiah (Rp).

## 6.1 Resource Cost

Labor cost is computed from APPROVED timesheets. Logged hours are converted to days (man-days) on an 8-hour-per-day basis, then multiplied by the resource's daily rate.

days (manday) = timesheet hours / 8

resourceCost = SUM( days x daily_rate ) for all APPROVED timesheets

Note: the rate used is the rate on the project assignment (ProjectResource); if absent, it falls back to the user's default daily rate.

## 6.2 Additional Cost

Non-labor costs (software, hardware, license, travel, other). Only APPROVED expenses count; PENDING/REJECTED items remain visible for transparency but do not add to cost.

additionalCost = SUM( amount ) for all APPROVED ProjectExpense

## 6.3 Actual Cost, Profit, and Margin

actualCost   = resourceCost + additionalCost

actualProfit = contractValue - actualCost

marginPct    = (actualProfit / contractValue) x 100

contractValue is the project's contract value. Margin is expressed as a percentage.

## 6.4 Accrued Cost

To monitor cost in flight, the application also computes accrued cost, which includes labor that is SUBMITTED but not yet approved.

accruedResourceCost = SUM( days x rate ) for APPROVED + SUBMITTED timesheets

accruedCost = accruedResourceCost + additionalCost

## 6.5 Fully-Loaded Cost (Overhead)

To reflect the company's indirect (overhead) cost, resource cost can be multiplied by a configurable overhead multiplier. This yields a more conservative 'net' cost and margin.

loadedResourceCost = resourceCost x overheadMultiplier

netActualCost   = loadedResourceCost + additionalCost

netActualProfit = revenueNet - netActualCost

netMarginPct    = (netActualProfit / revenueNet) x 100

## 6.6 Burn Rate & Revenue Recognition

Completion (burn rate) is measured from actual man-days versus planned man-days, capped at 100%. Revenue is recognized proportionally (following the percentage-of-completion principle / PSAK 72).

burnRatePct = min( (actualMan-days / plannedMan-days) x 100 , 100 )

recognizedRevenue = (burnRatePct / 100) x revenueNet

## 6.7 DPP & VAT (Tax Split)

The contract value may be VAT-inclusive or VAT-exclusive. DPP is the taxable base (net value), and VAT is computed from it. Default rate is 11%.

### If the value IS VAT-inclusive:

DPP   = value / (1 + vatRate/100) VAT   = value - DPP Total = value

### If the value is VAT-exclusive:

DPP   = value VAT   = value x (vatRate/100) Total = value + VAT

## 6.8 Payment Milestones (Billing)

Each project can be split into several milestones (Terms of Payment). Each milestone carries a percentage of the contract value (or a fixed amount), then split into DPP, VAT, and Total using the formulas in 6.7.

milestone_value = (percentage / 100) x contractValue   (or fixed amount if provided)

Validation: the application warns when the milestone percentages do not total 100%.

## 6.9 Invoice Numbering

Invoice numbers are allocated sequentially and uniquely with a year/month format, then a 4-digit sequence, for example:

INV/2026/06/0001 , INV/2026/06/0002 , ...

Numbers are allocated inside a race-safe transaction, so no duplicate numbers occur even when several invoices are created at once.

## 6.10 Cost Forecast

The forecast linearly projects final cost from the current burn rate. The financial endpoint aggregates approved timesheets per month and compares them against the contract value spread across the project's active months.

## 6.11 VAT Recap

The VAT recap sums all INVOICED and PAID invoices into a 12-month + annual breakdown for tax reporting.

## 6.12 Resource Utilization

Resource planning shows the manday load per week per person/business unit, accounting for leave (UserLeave). This is used to track consultant utilization and identify bench (idle capacity).

# 7. End-to-End Worked Example

Below is an illustrative set of numbers showing how all the formulas connect on a single project.

### Project assumptions

| Parameter | Value |
| --- | --- |
| Contract value (VAT-inclusive, 11%) | Rp 1,000,000,000 |
| Planned man-days | 100 days |
| Consultant A — daily rate | Rp 2,000,000 |
| Consultant A — approved timesheet | 320 hours (= 40 days) |
| Consultant B — daily rate | Rp 1,500,000 |
| Consultant B — approved timesheet | 160 hours (= 20 days) |
| Approved additional cost (license) | Rp 20,000,000 |
| Overhead multiplier (illustrative) | 1.30 |

### Computed results

| Component | Calculation | Result |
| --- | --- | --- |
| resourceCost | (40 x 2,000,000) + (20 x 1,500,000) | Rp 110,000,000 |
| additionalCost | approved license | Rp 20,000,000 |
| actualCost | 110,000,000 + 20,000,000 | Rp 130,000,000 |
| actualProfit | 1,000,000,000 - 130,000,000 | Rp 870,000,000 |
| marginPct | 870,000,000 / 1,000,000,000 x 100 | 87.0% |
| DPP (revenueNet) | 1,000,000,000 / 1.11 | Rp 900,900,900.90 |
| VAT | 1,000,000,000 - 900,900,900.90 | Rp 99,099,099.10 |
| burnRatePct | (60 / 100) x 100 | 60% |
| recognizedRevenue | 60% x 900,900,900.90 | Rp 540,540,540.54 |
| loadedResourceCost | 110,000,000 x 1.30 | Rp 143,000,000 |
| netActualCost | 143,000,000 + 20,000,000 | Rp 163,000,000 |
| netActualProfit | 900,900,900.90 - 163,000,000 | Rp 737,900,900.90 |
| netMarginPct | 737,900,900.90 / 900,900,900.90 x 100 | 81.9% |

### Billing milestone example

Milestone 1 = 30% of the contract value (VAT-inclusive):

| Component | Calculation | Result |
| --- | --- | --- |
| Milestone value (Total) | 30% x 1,000,000,000 | Rp 300,000,000 |
| DPP | 300,000,000 / 1.11 | Rp 270,270,270.27 |
| VAT | 300,000,000 - 270,270,270.27 | Rp 29,729,729.73 |

# 8. Accounting Integration (Xero)

The application connects two-way to Xero (accounting software): it pushes billing data out and pulls payment information back in.

- Invoice issuance — billing milestones are pushed as sales invoices (ACCREC) in Xero, including number, due date, and amount.

- Contact sync — client data is automatically created as a Xero Contact if it does not yet exist.

- Payment sync — payment status is pulled from Xero; a milestone is marked PAID only when Xero itself reports the invoice as fully paid.

- Outstanding & partial payments — the amount already paid and the remaining amount due are pulled from Xero for each invoice, so partial payments are visible per milestone instead of only a paid/unpaid flag.

- Invoice-number changes — if an invoice number is edited in Xero after it was issued, the updated number is synced back automatically so both systems stay consistent.

- Credit notes — any credit applied to an invoice in Xero (its credited amount) is pulled back and shown on the milestone, giving a true net position of paid + due + credited.

- Sync timing — payment data refreshes automatically every 30 minutes and on demand via the 'Sync from Xero' button (Management / Finance). Recently paid invoices keep syncing for up to 180 days, so later number edits or credit notes remain accurate.

Value accuracy: invoices are pushed tax-inclusive so the invoice total exactly matches the milestone value down to the cent (avoiding the 1-cent rounding drift seen previously).

# 9. Security & Access Control

- Token-based authentication (JWT) with hashed passwords (bcrypt).

- Role-based access control (RBAC) enforced on the server — not merely hidden in the UI.

- Data filtered by role (e.g. a PM only sees own projects; delivery roles see no financial figures).

- An audit trail (Activity) records important changes to projects and billing.

- The Xero integration uses OAuth2 with a signed state; invoice numbering is duplicate-safe.

# 10. Presentation Preparation & Demo Flow

### What to prepare

- A login account for each role you will demo (Management, PM, Sales, Consultant).

- One sample project already ACTIVE with timesheets, expenses, and billing milestones filled in.

- A storyline: from Sales intake -> PM planning -> consultant execution -> billing & Xero.

- This document as a handout, and an internet connection for the Xero demo (optional).

### Suggested demo flow (~15 minutes)

- Log in as Management — show the executive dashboard (KPIs, profit trend, at-risk projects).

- Open a project — walk through the Overview, Tasks (WBS/Gantt), and Resources tabs.

- Timesheets & Expenses tabs — show the approval flow and its effect on cost.

- Financials tab — show cost, margin, burn rate, and forecast updating automatically.

- Billing tab — create/view a milestone, then 'Send to Xero' to issue an invoice.

- Close with cross-project modules: Resource Planning, Reports, and VAT Recap.

### Key talking points

- "Margin is visible from day one, not only after the project ends."

- "Every cost figure comes from approved timesheets & expenses — not manual estimates."

- "Billing and VAT are automated, connected directly to accounting (Xero)."

- "Each role only sees what is relevant — financials are protected from the delivery team."