## Sheet1
[24 empty] | Anomalies |  |  | To be Invoice
[27 empty] | 2026-04-01 |  |  |  |  | 2026-05-01 |  |  |  | 2026-06-01 |  |  |  | 2026-07-01 |  |  |  |  | 2026-08-01 |  |  |  | 2026-09-01 |  |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  | 2026-12-01
Project | Customer | Project Number | Project manager | Target start date | Expected end date | Type | Stage | Selling amount | Invoiced | Remaining Invoice | Used hours | Budget Hours | Delta Hours | Used costs | Budget Costs | Delta Costs | Estimated Margin | Actual Margin | Delta Margin | Currency | PM comments | PMO In Charge | Updated/Not Updated in PSOhub (if applicable) | Unusual Margin | Zero Budget | PM | W14 (30-5) | W15 (6-12) | W16 (13-19) | W17 (20-26) | W18 (27-3) | W19 (4-10) | W20 (11-17) | W21 (18-24) | W22 (25-31) | W23 (1-7) | W24 (8-14) | W25 (15-21) | W26 (22-28) | W27 (29-5) | W28 (6-12) | W29 (13-19) | W30 (20-26) | W31 (27-2) | W32 (3-9) | W33 (10-16) | W34 (17-23) | W35 (24-30) | W36 (31-6) | W37 (7-13) | W38 (14-20) | W39 (21-27) | W40 (28-4) | W41 (5-11) | W42 (12-18) | W43 (19-25) | W44 (26-1) | W45 (2-8) | W46 (9-15) | W47 (16-22) | W48 (23-29) | W49 (30-6) | W50 (7-13) | W51 (14-20) | W52 (21-27) | W53 (28-3)
Bank - Pentest | Saspen | PRO-2026-483 | Andriko Perdana | 2026-04-07 |  | ITSEC - Offensive Security (VAPT / Red Teaming) | Active | 59400000 | 0 | 59400000 | 58.65 | 88 | -29.35 | 14030268.75 | 33226000 | -19195731.25 | 44.06% | 76.38% | 32.32% | IDR | The final invoice is contingent upon the 100% completion of remediation, as per the terms of the current contract. |  |  | Yes | No | PMO
Note on AB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @noventina@itsecasia.com please change it into week Assigned to noventina@itsecasia.com
Note on W3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @raihansyah@itsecasia.com please use this column to update the proper PM When done @noventina@itsecasia.com please download the new list for week 20 Assigned to raihansyah@itsecasia.com Reply: Hi Seb @sebastien@itsecasia.com , I have updated each project which has PMO in charge in PSOhub. You can see the status in column X. HI mbak Ventin @noventina@itsecasia.com you may proceed.